## Project Plan (hidden)
Capgemini Exceller - Industry Academia Collaboration
College : GLA Mathura ¦¦ SPOC: Mayank Srivastava |  | Project Start Date | Week # |  | Completed
TA SPOC: Akansha S ¦¦ CFMG SPOC: Virgin D / Pratik C |  | 2025-12-01 | 2 |  | In Progress
Training Partner: Bridgelabz ¦¦ SPOC: Jomy |  |  |  |  | Delayed
Business Unit: CCA ¦¦ SPOC: Shilpa S/ Vidya C
[6 empty] | 2025-12-12 |  |  |  |  | 2025-12-19 |  |  |  |  | 2025-12-26 |  |  |  |  | 2026-01-02 |  |  |  |  | 2026-01-09 |  |  |  |  | 2026-01-16 |  |  |  |  | 2026-01-23 |  |  |  |  | 2026-01-30 |  |  |  |  | 2026-02-06
TASKS | Start Date | End Dates | Duration | Status | %Complete | time axis 2025-12-08 to 2026-02-06
Project Summary | 2025-11-03 | 2026-06-08 | 156 day(s) |  | 83.64% | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
Phase 1 - Pre- Training | 2025-11-03 | 2025-12-23 | 37 day(s) |  | 92.17%
Requirement gathering - TOC Discussion | 2025-12-01 | 2025-12-05 | 5 | Completed | 90% | 2025-12-08: FALSE; 2025-12-09: FALSE; 2025-12-10: FALSE; 2025-12-11: FALSE; 2025-12-12: FALSE; 2025-12-15: FALSE; 2025-12-16: FALSE; 2025-12-17: FALSE; 2025-12-18: FALSE; 2025-12-19: FALSE; 2025-12-22: FALSE; 2025-12-23: FALSE; 2025-12-24: FALSE; 2025-12-25: FALSE; 2025-12-26: FALSE; 2025-12-29: FALSE; 2025-12-30: FALSE
TOC signoff | 2025-12-12 | 2025-12-15 | 2 day(s) | Delayed | 63%
College Exam Update | 2025-11-03 | 2025-11-28 | 20 day(s) | Completed | 100%
Expectation setting with College & Training Partner (Virtual) | 2025-12-22 | 2025-12-22 | 1 day(s) | Completed | 100%
Distribution of document with College - Logistics readiness and Candidature disqualification | 2025-12-23 | 2025-12-23 | 1 day(s) | Completed | 100%
Meeting with College and Training Partner (In-Person) | 2025-12-22 | 2025-12-22 | 1 day(s) | Completed | 100%
Phase 2 - Training and Engagment | 2025-12-12 | 2026-06-08 |  |  | 58.75%
Creation of Assessment Framework | 2025-12-12 | 2025-12-30 | 13 day(s) | Completed | 100%
Training Start and End - Technical | 2025-12-16 | 2026-06-08 | 125 day(s) | Completed | 100%
Training Start and End - Powerskills |  |  |  | Completed | 100%
Training Kickoff with Stakeholders (College, Students, BU, Training Partners) |  |  |  | Completed | 100%
In-Person Visit - Orientation session by BU SME/Leader |  |  |  | Delayed | 80%
Weekly connect with Students and BU (Virtual) | 2025-12-22 | 2026-01-01 | 9 day(s) | In Progress | 100%
Weekly connect with Training Partner and BU (Virtual) |  |  |  | Completed | 100%
L&D Audit -Quality Check |  |  |  | Completed | 100%
Masterclass - I |  |  |  | In Progress | 10%
Module 1 Assessment |  |  |  | In Progress | 10%
Psychometric Test |  |  |  | In Progress | 10%
Masterclass - II |  |  |  | In Progress | 90%
L&D Audit -Quality Check |  |  |  | In Progress | 10%
Sprint (BU Presence) |  |  |  | In Progress | 10%
L1 Assessment |  |  |  | In Progress | 10%
Result Declaration to college |  |  |  | In Progress | 10%
Phase 3 - Post Training |  |  |  |  | 100%
Tentative Onboarding Plan ( starting month) |  |  |  | Completed | 100%
Post training - Engagment plan - Training Partner and BU Interventions |  |  |  | Completed | 100%
Formulas:
Project Start Date = IF(MAX([Project Start Date, row below]:D38)>0,MAX([Project Start Date, row below]:D38),"")
Week # = IF(OR(C11="",[Project Start Date]=""),"",NETWORKDAYS(C11,[Project Start Date])& " day(s)")
Week # = IF(OR(C13="",[Project Start Date]=""),"",NETWORKDAYS(C13,[Project Start Date]))

## Instructions (hidden)
Field Name
Project Start Date | Mandatory , To be updated manually
Start Date | Mandatory , To be updated manually
Planned End Date | Mandatory , To be updated manually
Actual End date | Mandatory , To be updated manually
Days | Autocalculated
Status | To be updated as: (Mandatory, to be updated Manually)
Not started | Planned , but yet to start , %Complete column should show 0%
In Progress | % Completion column should reflect between 1%-99%. % to be updated manually
Complete | % Completion column should reflect 100%, it should be updated manually
Delayed | % Completion column should reflect between 1%-99%. % to be updated manually
Deferred | indicates the task was postponed and then completed., hence % Completion column should reflect 100% once completed
Column I onwards | Autocalculated
If any task is not captured and if its relevant for your Business Unit, please feel free to add under respective phases. Don’t forget to copy formulas from cells above

## Team List-FS
Sno | Superset ID | Email | Name | Hiring Status | Business Unit Tag | Gender | BU Cohort | CFMG_Practice | Technology | Group Wise Segregation | Assigned Rooms
1 | 6391000 | ayushsi.9931@gmail.com | Ayush Singh | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
2 | 6394028 | surajrawal228@gmail.com | Suraj Singh Rawal | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
3 | 6396143 | amanraj15112003@gmail.com | Aman Kumar | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
4 | 6397645 | gunguns618@gmail.com | Gungun Singh | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
5 | 6398275 | anushka.22scse1050007@galgotiasuniversity.edu.in | Anushka Singh | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
6 | 6398348 | somya.22scse1011259@galgotiasuniversity.edu.in | Somya Mishra | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
7 | 6398700 | rachit.22scse1280088@galgotiasuniversity.edu.in | Rachit Kumar | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
8 | 6399028 | thakuraloksingh936917@gmail.com | Alok Kumar Singh | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
9 | 6400982 | nidhi.22scse1011706@galgotiasuniversity.edu.in | Nidhi Adhikari | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
10 | 6401895 | sourav.22scse1012424@galgotiasuniversity.edu.in | Sourav Joshi | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
11 | 6411609 | aditi.22scse1010687@galgotiasuniversity.edu.in | Aditi Gupta | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
12 | 6411704 | aniket.22scse1011967@galgotiasuniversity.edu.in | ANIKET KUMAR THAKUR | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
13 | 6411996 | viraj.22scse1011292@galgotiasuniversity.edu.in | Viraj Kumar | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
14 | 6415881 | khushirana122004@gmail.com | Khushi | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
15 | 6433095 | aman.22scse1011386@galgotiasuniversity.edu.in | Aman Patel | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
16 | 6433507 | krishnapratapsingh700@gmail.com | Krishna Pratap Singh | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
17 | 6732091 | shalini.22gcebcsaiml031@galgotiacollege.edu | Shalini Gupta | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
18 | 6732301 | manas.22gcebds054@galgotiacollege.edu | Manas Pratap Singh | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
19 | 6732434 | choudharyisha2003@gmail.com | Isha Choudhary | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
20 | 6732452 | shubham.22gcebec148@galgotiacollege.edu | Shubham Prajapati | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
21 | 6732560 | om30arora@gmail.com | Om Arora | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
22 | 6732579 | ijavedofficial@gmail.com | Mohammad Javed | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
23 | 6733792 | amansanidhya9876@gmail.com | Sanidhya Singh | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
24 | 6735162 | rakeshmundel000@gmail.com | Rakesh Mundel | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
25 | 6735619 | alihibban78@gmail.com | Mohammad Hibban Ali | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
26 | 6736303 | khushi.22gcebec090@galgotiacollege.edu | Khushi Ranjan | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
27 | 6736484 | snehagoyal0110@gmail.com | Sneha Goyal | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
28 | 6736534 | tomaranurag375@gmail.com | Anurag Tomar | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
29 | 6740282 | ishank.22gcebcs220@galgotiacollege.edu | ishank | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
30 | 6742417 | vishaluser7651@gmail.com | Vishal Yadav | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
31 | 6745465 | thritik1713@gmail.com | Hritik Tiwari | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
32 | 6745657 | aakanshigarg62@gmail.com | Aakanshi Garg | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
33 | 6755766 | tychephp@gmail.com | Shravani Saloni Jaiswal | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
34 | 6755876 | gargchaitanya22@gmail.com | Chaitanya Garg | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
35 | 6756551 | ishaanpatel29976@gmail.com | Ishaan Patel | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
36 | 6762501 | parthsaxena182512@gmail.com | Parth Saxena | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
37 | 6764036 | yashashvisingh2004@gmail.com | Yashashvi Singh | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
38 | 6766259 | uns.singh03@gmail.com | Ujjwal Narayan Singh | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
39 | 6784574 | pushpendra99x@gmail.com | Pushpendra Kushwaha | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
40 | 6786333 | youknowprashant@gmail.com | Prashant Singh | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-1 | L02, AI Block, GU
41 | 6786566 | sachinmishra29122003@gmail.com | Sachin Mishra | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
42 | 5026258 | aman.22scse1010706@galgotiasuniversity.edu.in | Aman Kumar Yadav | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
43 | 5027477 | sushantjha1205@gmail.com | Sushant Kumar Jha | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
44 | 6391155 | ishita.22scse1410038@galgotiasuniversity.edu.in | Ishita Chauhan | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
45 | 6391774 | gbhatt570@gmail.com | Gaurav Bhatt | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
46 | 6392501 | dreamsalive404@gmail.com | Pushpraj Upadhyay | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
47 | 6394098 | dskter.sahil@gmail.com | Sahil Prajapati | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
48 | 6394654 | lakshaybofficial@gmail.com | Lakshay Bhandari | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
49 | 6395480 | ratnesh.22scse1011240@galgotiasuniversity.edu.in | Ratnesh Rai | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
50 | 6395693 | pranav.22scse1011200@galgotiasuniversity.edu.in | Pranav Pandey | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
51 | 6397906 | sainimahak328@gmail.com | Mahak Saini | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
52 | 6398255 | dev.devanshseth.engg0072@gmail.com | Devansh Seth | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
53 | 6398319 | ayush.22scse1011391@galgotiasuniversity.edu.in | Ayush Tiwari | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
54 | 6398327 | ayushi.22scse1010299@galgotiasuniversity.edu.in | Ayushi Shrivastava | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
55 | 6398844 | unnati.22scse1010511@galgotiasuniversity.edu.in | Unnati Bhardwaj | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
56 | 6401955 | shiwangi.22scse1410008@galgotiasuniversity.edu.in | Shiwangi Upadhyay | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
57 | 6402672 | abhaypratap1968@gmail.com | Abhay Pratap Singh | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
58 | 6405683 | shreya.22scse1420032@galgotiasuniversity.edu.in | Shreya Singh | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
59 | 6405772 | kadi93030@gmail.com | Aditya Kumar | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
60 | 6406093 | harshita.22scse1012593@galgotiasuniversity.edu.in | Harshita Gahlot | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
61 | 6410054 | ritika.22scse1012602@galgotiasuniversity.edu.in | Ritika Ghosh | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
62 | 6410291 | pawan.22scse1010322@galgotiasuniversity.edu.in | Pawan Kumar Singh | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
63 | 6410657 | ayush.22scse1012342@galgotiasuniversity.edu.in | Ayush Singh | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
64 | 6412748 | ayush.22scse1010380@galgotiasuniversity.edu.in | Ayush Kumar | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
65 | 6413501 | aditya.22scse1011178@galgotiasuniversity.edu.in | Aditya Singh | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
66 | 6416684 | rhythm.22scse1010679@galgotiasuniversity.edu.in | Rhythm Gupta | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
67 | 6417254 | surya.22scse1011183@galgotiasuniversity.edu.in | Surya Pratap Singh | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
68 | 6419190 | utkarsh.bhola31@gmail.com | Utkarsh Bhola | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
69 | 6424622 | disha.22scse1140022@galgotiasuniversity.edu.in | Disha Tomar | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
70 | 6433522 | anshikarai0804@gmail.com | Anshika Rai | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
71 | 6433613 | mayankyadav7618@gmail.com | Mayank Yadav | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
72 | 6732015 | anushkamathur2107@gmail.com | Anushka Mathur | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
73 | 6734969 | vaduni.22gcebcs167@galgotiacollege.edu | Vaduni Niranjan | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
74 | 6735843 | sggupta548@gmail.com | Saurabh Gupta | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
75 | 6736373 | khushi.22gcebcs013@galgotiacollege.edu | Khushi Mahto | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
76 | 6736535 | divyansh.22gcebcsaiml038@galgotiacollege.edu | Divyansh Yagyik | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
77 | 6737716 | navneetdhardubey.india@gmail.com | Navneet Dhar | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
78 | 6737918 | shubhplace084@gmail.com | Shubham Pandey | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
79 | 6739889 | shivam010803@gmail.com | Shivam Verma | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
80 | 6740603 | sourav.22gcebaiml061@galgotiacollege.edu | Sourav Pandey | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
81 | 6747183 | bhavya.22gcebds064@galgotiacollege.edu | Bhavya Jaiswal | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-2 | L06, AI Block, GU
82 | 6755736 | jatinjaisinghrathore@gmail.com | Jatin Jai Singh Rathore | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
83 | 6756193 | shivamgupta842309@gmail.com | Shivam Gupta | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
84 | 6757784 | sakshi.22scse1012860@galgotiasuniversity.edu.in | Sakshi Kumari | Final Select | FS_DCX | FEMALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
85 | 6758101 | sakshamagrahari932@gmail.com | Saksham Agrahari | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
86 | 6763543 | shivamguptavns01@gmail.com | Shivam Gupta | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
87 | 6771839 | vinay.22scse1011121@galgotiasuniversity.edu.in | Vinay Kumar | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
88 | 6814410 | ritwik1607@gmail.com | Ritwik Chandra | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
89 | 6825163 | rhythm.24scse2030245@galgotiasuniversity.ac.in | Rhythm Gulati | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
90 | 7131121 | sankalpsachan10@gmail.com | sankalp sachan | Final Select | FS_DCX | MALE | FS | FS_DCX | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
91 | 6731818 | katiyarashtam014@gmail.com | Ashtam Katiyar | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
92 | 6732070 | amansinghyadav876@gmail.com | Aman Singh Yadav | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
93 | 6732080 | aarush1998@gmail.com | Aarush Gupta | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
94 | 6732370 | yogendra.22gcebcs086@galgotiacollege.edu | Yogendra Kumar Maurya | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
95 | 6734152 | vedantbaliyan123@gmail.com | VEDANT BALIYAN | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
96 | 6734638 | nikhilkush906@gmail.com | Nikhil Kushwah | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
97 | 6735086 | priyakinha153@gmail.com | Priya | Final Select | SOGETI | FEMALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
98 | 6736175 | shreshthagupta79@gmail.com | Shreshtha Gupta | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
99 | 6736522 | abhigyantripathi42@gmail.com | Abhigyan Tripathi | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
100 | 6755875 | deep2004gupta@gmail.com | Deep Gupta | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
101 | 6756405 | raiayush913@gmail.com | Ayush Kumar Rai | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
102 | 6757962 | adityaraj4160@gmail.com | Aditya Raj | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
103 | 6763542 | mohd.22gcebit127@galgotiacollege.edu | MOHD SADIQUE | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
104 | 6899837 | samarwats@gmail.com | Samar Pratap Singh Wats | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
105 | 7131296 | chaudharyayush028@gmail.com | Ayush Chaudhary | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
106 | 7135004 | balrajkv666@gmail.com | Balraj | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
107 | 6433490 | sid068159@gmail.com | Siddhant Singh | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
108 | 6731730 | smadeshiya491@gmail.com | Sahil Madeshiya | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
109 | 6732097 | mahijhs14@gmail.com | Mahi Sahu | Final Select | SOGETI | FEMALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
110 | 6732491 | saraswatpragya4@gmail.com | Pragya Saraswat | Final Select | SOGETI | FEMALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
111 | 6732510 | ddeependra2004@gmail.com | Deependra Verma | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
112 | 6735969 | anant.22gcebcs035@galgotiacollege.edu | Anant Singh | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
113 | 6736550 | nainasingh.he143@gmail.com | Naina | Final Select | SOGETI | FEMALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
114 | 6738161 | jaladhi.22gceben079@galgotiacollege.edu | Jaladhi Shrivastava | Final Select | SOGETI | FEMALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
115 | 6741320 | gkhushi2901@gmail.com | Khushi Gupta | Final Select | SOGETI | FEMALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
116 | 6755685 | yogesh.22gcebai078@galgotiacollege.edu | Yogesh Kumar | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
117 | 6763686 | Shreyasonii181@gmail.com | Shreya Soni | Final Select | SOGETI | FEMALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
118 | 6772158 | luvgupta2020@gmail.com | Luv Kumar | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
119 | 6810353 | roymansi911@gmail.com | MANSI ROY | Final Select | SOGETI | FEMALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
120 | 6813364 | shubhi.sa24@gmail.com | Shubhi Awasthi | Final Select | SOGETI | FEMALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU
121 | 7134185 | romimaindola9411@gmail.com | ROMI MAINDOLA | Final Select | SOGETI | MALE | Sogeti | SOGETI | Java Foundation TOC_ 40 Days | Group-3 | L07, AI Block, GU

## Team List-Sogeti
S. No. | Candidate Superset ID | Candidate name | Email ID | BU | Technology | Assigned room
1 | 6784944 | Sanskriti Saurabh | sanskriti.24scse2240036@galgotiasuniversity.ac.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
2 | 6437947 | Vivek Shrotriya | vivek.22SCSE1011902@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
3 | 6432705 | Kushagra Chandra | kushagra.22scse1011704@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
4 | 6422829 | Saurabh Yadav | saurabh.22scse1010953@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
5 | 6412774 | Agraj Mishra | agrajmishra60@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
6 | 6404281 | Vanshika Gangwar | vanshika.22scse1011113@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
7 | 6401588 | PRIYANSHU KUMAR SAH | priyanshukumarsah03@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
8 | 6401087 | Shruti Mishra | shruti.22scse1010883@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
9 | 6400859 | Shabbu Parveen | shabbuparveen377@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
10 | 6400724 | kumar jaywardhan | kumar.22scse1010226@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
11 | 6400112 | Ayush Kumar | ayush.22scse1010411@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
12 | 6399543 | Aman Ansari | one.aman99@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
13 | 6398306 | Chandransu | rishpandey59@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
14 | 6398245 | Mohammad Ahmad Siddiqui | ahmadofficial1806@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
15 | 6397364 | ankit raj | ankit.22scse1012422@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
16 | 6396966 | NAINA MITTAL | nainamittal063@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
17 | 6394706 | Prince Dixit | prince.22scse1010046@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
18 | 6391735 | Priyanshu Kumar | priyanshuchaudhary194@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
19 | 6391219 | Himanshu Chaurasiya | himanshu.22scse1011498@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
20 | 5027213 | Daksh Sharma | daksh.22scse1010203@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
21 | 7116051 | Aryan | ramoyd926@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
22 | 6758587 | Kirti Singh | kirti.22scse1012550@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
23 | 6755834 | Vaibhav Gupta | leindiangrandeur@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
24 | 6434797 | Shivank singh chandel | singhshivank72@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
25 | 6433735 | Mohammad Ayan | mohammad.ayan9450@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
26 | 6430994 | Archana Maurya | archanamaurya382003@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
27 | 6430286 | Piyush Kumar | piyush.22scse1011310@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
28 | 6419785 | Satyam Kumar | satyam.22scse1010799@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
29 | 6419648 | Anshu Nagar | cangujjar@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
30 | 6416851 | SIDDHARTH | siddhucaa@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
31 | 6413621 | AMAN KUMAR SINGH | aman.22scse1180232@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
32 | 6413483 | Ravi Kumar Tiwari | ravirkt0@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
33 | 6412630 | Harshita Dwivedi | harshitadwivedi.2210@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
34 | 6412396 | Ishika Chakraborty | chakrabortyishika64@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
35 | 6411390 | Ankit Raj | raj.ankit5176@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
36 | 6410948 | Arnav Chauhan | arnav.22scse1012818@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
37 | 6406264 | Vandana Srivastava | vandana.22scse1012894@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
38 | 6405698 | Nikhil Tripathi | nikhiltripathi2511@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
39 | 6400955 | Mrinal Mayank | krish404147@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
40 | 6399135 | Priyadarshani | priyadarshani.22scse1011554@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
41 | 6399051 | Shivendera Pratap Singh | shivendera.22scse1010967@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
42 | 6398773 | Arjun Pal | arjun.22scse1010202@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
43 | 6398521 | Aditya Kumar | aditya.22scse1011313@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
44 | 6398445 | PRIYANSHU MALL | ps437999@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
45 | 6398287 | Shivam Rawal | shivam.22scse1010893@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
46 | 6398253 | Aman Raj | 28amanraj@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
47 | 6398235 | Divyansh saxena | divyanshsaxena12123@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
48 | 6396984 | Anish Umar | anishumar786@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
49 | 6395553 | Harshit Mishra | harshit.22scse1012270@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
50 | 6394488 | Chandra Bhushan Sah | chandrabhushan.sah15@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
51 | 6392312 | Poorendra Mishra | poorendra.22scse1011713@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
52 | 5026498 | Himani Singh | himani.22scse1012643@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
53 | 5025465 | Prince Tomer | prince.22scse1010280@galgotiasuniversity.edu.in | Sogeti | Track T5 - Data & AI | L01, AI Block, GU
54 | 6401439 | Mohika Grover | mohikagrover2018@gmail.com | Sogeti | Track T5 - Data & AI | L01, AI Block, GU

## Training Calendar-FS
Qspiders Assessment will be provided on every Saturdays
Batch Name | Topic | Detailed concepts | Duration | Start date | End Date | Trainer Type | Training Mode | Trainer Name
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Java overview, JVM, datatypes, variables, literals | 1 | 2026-01-12 | 2026-01-12
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Operators, assignments, control statements | 1 | 2026-01-13 | 2026-01-13
Java Foundation Batch Jan 2026 | Programming Foundation with Java | HOLIDAY | 1 | 2026-01-14 | 2026-01-14
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Loops, break and continue, problem solving | 1 | 2026-01-15 | 2026-01-15
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Arrays (1D, 2D), initialization, passing arrays | 1 | 2026-01-16 | 2026-01-16
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-01-17 | 2026-01-17
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-01-18 | 2026-01-18
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Strings, String methods, StringBuilder vs StringBuffer | 1 | 2026-01-19 | 2026-01-19
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Classes, objects, constructors, overloading | 1 | 2026-01-20 | 2026-01-20
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Encapsulation and abstraction | 1 | 2026-01-21 | 2026-01-21
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Inheritance (IS-A, HAS-A), polymorphism | 1 | 2026-01-22 | 2026-01-22
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Method overriding, casting, interfaces | 1 | 2026-01-23 | 2026-01-23
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-01-24 | 2026-01-24
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-01-25 | 2026-01-25
Java Foundation Batch Jan 2026 |  | HOLIDAY | 1 | 2026-01-26 | 2026-01-26
Java Foundation Batch Jan 2026 | Power Skill 1 | Introduction to Power skills # Ice breaking, Objective setting # Communication skills (Modes and overview) # Introduction to written communication (dos and don’ts of emails) # Grooming (Hygiene Squad) | 1 | 2026-01-27 | 2026-01-27
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Access modifiers, static members, enums | 1 | 2026-01-28 | 2026-01-28
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Wrapper classes, autoboxing, garbage collection | 1 | 2026-01-29 | 2026-01-29
Java Foundation Batch Jan 2026 | Programming Foundation with Java | equals() and hashCode() | 1 | 2026-01-30 | 2026-01-30
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-01-31 | 2026-01-31
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-02-01 | 2026-02-01
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Collections framework overview, List, ArrayList | 1 | 2026-02-02 | 2026-02-02
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Set, Map, Queue, sorting collections | 1 | 2026-02-03 | 2026-02-03
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Generics and generics with collections | 1 | 2026-02-04 | 2026-02-04
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Layered architecture | 1 | 2026-02-05 | 2026-02-05
Java Foundation Batch Jan 2026 | Programming Foundation with Java | Design patterns: DAO, DTO, Iterator | 1 | 2026-02-06 | 2026-02-06
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-02-07 | 2026-02-07
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-02-08 | 2026-02-08
Java Foundation Batch Jan 2026 | Programming Foundation with Java | End-to-end Java consolidation (OOP + Collections) | 1 | 2026-02-09 | 2026-02-09
Java Foundation Batch Jan 2026 | Problem Solving and Data Structure with Java | DSA introduction, time and space complexity | 1 | 2026-02-10 | 2026-02-10
Java Foundation Batch Jan 2026 | Power Skill 2 | Language skills (Part1) # Introduction to parts of speech & Subject verb agreement and Articles # Content videos # Email Etiquette # Test(Email- application of SVA & Articles). # Activity bases learnings (role play activity) # Listening (questioning and probing) Language skills (Part2) # Tenses # Art of pronunciation (verbal’s skills) #using Co-pilot and ChatGPT | 1 | 2026-02-11 | 2026-02-11
Java Foundation Batch Jan 2026 | Problem Solving and Data Structure with Java | Arrays: traversal, insertion, deletion | 1 | 2026-02-12 | 2026-02-12
Java Foundation Batch Jan 2026 | Problem Solving and Data Structure with Java | Arrays and strings problems | 1 | 2026-02-13 | 2026-02-13
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-02-14 | 2026-02-14
Java Foundation Batch Jan 2026 | SUNDAY | HOLIDAY |  | 2026-02-15 | 2026-02-15
Java Foundation Batch Jan 2026 | Problem Solving and Data Structure with Java | Stack implementation and problems | 1 | 2026-02-16 | 2026-02-16
Java Foundation Batch Jan 2026 | Problem Solving and Data Structure with Java | Queue implementation and use cases | 1 | 2026-02-17 | 2026-02-17
Java Foundation Batch Jan 2026 | Problem Solving and Data Structure with Java | Searching techniques | 1 | 2026-02-18 | 2026-02-18
Java Foundation Batch Jan 2026 | Problem Solving and Data Structure with Java | Sorting techniques and comparison | 1 | 2026-02-19 | 2026-02-19
Java Foundation Batch Jan 2026 | Problem Solving and Data Structure with Java | Advanced array problems | 1 | 2026-02-20 | 2026-02-20
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-02-21 | 2026-02-21
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-02-22 | 2026-02-22
Java Foundation Batch Jan 2026 | Problem Solving and Data Structure with Java | Dynamic programming basics, Knapsack | 1 | 2026-02-23 | 2026-02-23
Java Foundation Batch Jan 2026 | Problem Solving and Data Structure with Java | LCS, Coin change, Greedy algorithms | 1 | 2026-02-24 | 2026-02-24
Java Foundation Batch Jan 2026 | Problem Solving and Data Structure with Java | Heap and Priority Queue | 1 | 2026-02-25 | 2026-02-25
Java Foundation Batch Jan 2026 | Problem Solving and Data Structure with Java + Sprint 1 Evaluation (Automated) | Hashing problems | 1 | 2026-02-26 | 2026-02-26
Java Foundation Batch Jan 2026 | HackerRank Preparation |  | 1 | 2026-02-27 | 2026-02-27
Java Foundation Batch Jan 2026 | HackerRank Preparation |  | 1 | 2026-02-28 | 2026-02-28
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-03-01 | 2026-03-01
Java Foundation Batch Jan 2026 |  | HOLIDAY |  | 2026-03-02 | 2026-03-02
Java Foundation Batch Jan 2026 | HackerRank Test |  | 1 | 2026-03-03 | 2026-03-03
Java Foundation Batch Jan 2026 |  | HOLIDAY |  | 2026-03-04 | 2026-03-04
Java Foundation Batch Jan 2026 | Power Skill 3 | Presentation skills # Introduction to Presentation skills (setting objective) # Albert Mehrabian rule and communication styles # Rules of presentation (3 T’s) # Dos and Don’ts of presentation # Activity on presentation skills by YP’s | 1 | 2026-03-05 | 2026-03-05
Java Foundation Batch Jan 2026 | Advance Concepts in Java | Lambda expressions and functional interfaces | 1 | 2026-03-06 | 2026-03-06
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-03-07 | 2026-03-07
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-03-08 | 2026-03-08
Java Foundation Batch Jan 2026 | Advance Concepts in Java | Stream API with collections | 1 | 2026-03-09 | 2026-03-09
Java Foundation Batch Jan 2026 | Advance Concepts in Java | Multithreading basics and lifecycle | 1 | 2026-03-10 | 2026-03-10
Java Foundation Batch Jan 2026 | Advance Concepts in Java | Synchronization, deadlock, thread communication | 1 | 2026-03-11 | 2026-03-11
Java Foundation Batch Jan 2026 | Advance Concepts in Java | File handling and I/O streams | 1 | 2026-03-12 | 2026-03-12
Java Foundation Batch Jan 2026 | Advance Concepts in Java | Exception handling and custom exceptions | 1 | 2026-03-13 | 2026-03-13
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-03-14 | 2026-03-14
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-03-15 | 2026-03-15
Java Foundation Batch Jan 2026 | Advance Concepts in Java + Sprint 2 Evaluation (Automated) | JUnit 5 concepts and lifecycle,Mockito and TDD workflow | 1 | 2026-03-16 | 2026-03-16
Java Foundation Batch Jan 2026 | Database and SQL | RDBMS concepts, PostgreSQL, SELECT | 1 | 2026-03-17 | 2026-03-17
Java Foundation Batch Jan 2026 | Database and SQL | WHERE, ORDER BY, GROUP BY, HAVING | 1 | 2026-03-18 | 2026-03-18
Java Foundation Batch Jan 2026 | Database and SQL | Joins | 1 | 2026-03-19 | 2026-03-19
Java Foundation Batch Jan 2026 | Database and SQL | DDL, constraints, keys | 1 | 2026-03-20 | 2026-03-20
Java Foundation Batch Jan 2026 |  | HOLIDAY |  | 2026-03-21 | 2026-03-21
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-03-22 | 2026-03-22
Java Foundation Batch Jan 2026 | Power Skill 4 | Email communication # Objective setting on written communication # 7C’s (Email etiquette) # Email writing Test and activities # Accountability & Ownership # Teamwork | 1 | 2026-03-23 | 2026-03-23
Java Foundation Batch Jan 2026 | Database and SQL | Complex SQL queries and joins | 1 | 2026-03-24 | 2026-03-24
Java Foundation Batch Jan 2026 | JDBC + JPA with Hibernate | JDBC overview, drivers, connections | 1 | 2026-03-25 | 2026-03-25
Java Foundation Batch Jan 2026 |  | HOLIDAY |  | 2026-03-26 | 2026-03-26
Java Foundation Batch Jan 2026 | JDBC + JPA with Hibernate | Statement, PreparedStatement, ResultSet | 1 | 2026-03-27 | 2026-03-27
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-03-28 | 2026-03-28
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-03-29 | 2026-03-29
Java Foundation Batch Jan 2026 | JDBC + JPA with Hibernate | JPA and ORM concepts, entities | 1 | 2026-03-30 | 2026-03-30
Java Foundation Batch Jan 2026 |  | HOLIDAY |  | 2026-03-31 | 2026-03-31
Java Foundation Batch Jan 2026 | JDBC + JPA with Hibernate | Entity lifecycle and relationships | 1 | 2026-04-01 | 2026-04-01
Java Foundation Batch Jan 2026 | Power Skill 5 | Team work and accountability # Listening, Questioning & Probing # Meeting Etiquette # Interview Skills #Comprehensive Test (Email, Grammar, Behavioural) | 1 | 2026-04-02 | 2026-04-02
Java Foundation Batch Jan 2026 |  | HOLIDAY |  | 2026-04-03 | 2026-04-03
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-04-04 | 2026-04-04
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-04-05 | 2026-04-05
Java Foundation Batch Jan 2026 | JDBC + JPA with Hibernate | JPQL and Criteria API | 1 | 2026-04-06 | 2026-04-06
Java Foundation Batch Jan 2026 | JDBC + JPA with Hibernate | Hibernate integration and mappings | 1 | 2026-04-07 | 2026-04-07
Java Foundation Batch Jan 2026 | DevOps | DevOps concepts and CI/CD pipeline | 1 | 2026-04-08 | 2026-04-08
Java Foundation Batch Jan 2026 | DevOps | Git and GitHub (local and remote) | 1 | 2026-04-09 | 2026-04-09
Java Foundation Batch Jan 2026 | DevOps | Jenkins jobs and Git integration | 1 | 2026-04-10 | 2026-04-10
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-04-11 | 2026-04-11
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-04-12 | 2026-04-12
Java Foundation Batch Jan 2026 | DevOps | Jenkins with Maven and JUnit | 1 | 2026-04-13 | 2026-04-13
Java Foundation Batch Jan 2026 |  | HOLIDAY |  | 2026-04-14 | 2026-04-14
Java Foundation Batch Jan 2026 | DevOps | SonarQube and Maven lifecycle | 1 | 2026-04-15 | 2026-04-15
Java Foundation Batch Jan 2026 | DevOps | End-to-end CI/CD workflow | 1 | 2026-04-16 | 2026-04-16
Java Foundation Batch Jan 2026 | Spring 5.0 | Spring Core overview, IoC, DI concepts, loose coupling | 1 | 2026-04-17 | 2026-04-17
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-04-18 | 2026-04-18
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-04-19 | 2026-04-19
Java Foundation Batch Jan 2026 | Spring 5.0 | Spring container, bean lifecycle, autowiring modes | 1 | 2026-04-20 | 2026-04-20
Java Foundation Batch Jan 2026 | Spring 5.0 | Java-based configuration, annotation configuration (@Configuration, @Component, @Autowired, component scanning) | 1 | 2026-04-21 | 2026-04-21
Java Foundation Batch Jan 2026 | Spring 5.0 | Spring Boot introduction, starters, application structure, @SpringBootApplication, Boot lifecycle | 1 | 2026-04-22 | 2026-04-22
Java Foundation Batch Jan 2026 | Spring 5.0 | Spring Boot configuration, application.properties, externalized configuration, profiles | 1 | 2026-04-23 | 2026-04-23
Java Foundation Batch Jan 2026 | Spring 5.0 | REST fundamentals, REST architecture, @RestController, @RequestMapping | 1 | 2026-04-24 | 2026-04-24
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-04-25 | 2026-04-25
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-04-26 | 2026-04-26
Java Foundation Batch Jan 2026 | Spring 5.0 | REST annotations: @GetMapping, @PostMapping, @PathVariable, @RequestParam, JSON/XML handling | 1 | 2026-04-27 | 2026-04-27
Java Foundation Batch Jan 2026 | Spring 5.0 | Spring Data JPA introduction, ORM recap, @Entity, @Id, basic mappings | 1 | 2026-04-28 | 2026-04-28
Java Foundation Batch Jan 2026 | Spring 5.0 | Repository interfaces, query methods, derived queries, JPQL overview | 1 | 2026-04-29 | 2026-04-29
Java Foundation Batch Jan 2026 | Spring 5.0 | Transactions, persistence context, @Transactional, cascading | 1 | 2026-04-30 | 2026-04-30
Java Foundation Batch Jan 2026 | Spring 5.0 |  | 1 | 2026-05-01 | 2026-05-01
Java Foundation Batch Jan 2026 | Revision |  | 1 | 2026-05-02 | 2026-05-02
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-05-03 | 2026-05-03
Java Foundation Batch Jan 2026 | Spring 5.0 | Spring Data REST introduction, repository exposure, HTTP methods, Postman usage | 1 | 2026-05-04 | 2026-05-04
Java Foundation Batch Jan 2026 | Spring 5.0 | API documentation using Swagger, request/response validation | 1 | 2026-05-05 | 2026-05-05
Java Foundation Batch Jan 2026 | Spring 5.0 | Global exception handling, @ControllerAdvice, @ExceptionHandler, REST error responses | 1 | 2026-05-06 | 2026-05-06
Java Foundation Batch Jan 2026 | Sprint 3 Implementation |  | 1 | 2026-05-07 | 2026-05-07
Java Foundation Batch Jan 2026 | Sprint 3 Implementation |  | 1 | 2026-05-08 | 2026-05-08
Java Foundation Batch Jan 2026 | Sprint 3 Implementation |  | 1 | 2026-05-09 | 2026-05-09
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-05-10 | 2026-05-10
Java Foundation Batch Jan 2026 | Sprint 3 Implementation |  | 1 | 2026-05-11 | 2026-05-11
Java Foundation Batch Jan 2026 | Sprint 3 Implementation |  | 1 | 2026-05-12 | 2026-05-12
Java Foundation Batch Jan 2026 | Sprint 3 Implementation |  | 1 | 2026-05-13 | 2026-05-13
Java Foundation Batch Jan 2026 | Sprint 3 Implementation |  | 1 | 2026-05-14 | 2026-05-14
Java Foundation Batch Jan 2026 | Sprint 3 Evaluation |  | 1 | 2026-05-15 | 2026-05-15
Java Foundation Batch Jan 2026 | L1 Preparation |  | 1 | 2026-05-16 | 2026-05-16
Java Foundation Batch Jan 2026 | SUNDAY |  |  | 2026-05-17 | 2026-05-17
Java Foundation Batch Jan 2026 | L1 Test |  | 1 | 2026-05-18 | 2026-05-18
102

## Training Calendar-Sogeti
Batch Name | Topic | Detailed concepts | Duration | Start date | End Date | Trainer Type | Training Mode | Trainer Name
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Python Introduction & Scripting Python overview & use cases Installing Python & IDE setup Python syntax, variables Writing and executing scripts | 1 | 2026-01-12 | 2026-01-12
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Data Types Numbers, strings Lists, tuples, sets, dictionaries Type casting & basic operations | 1 | 2026-01-13 | 2026-01-13
Left Shift Program 2026 | HOLIDAY |  | 0 | 2026-01-14 | 2026-01-14
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Control Flow Conditional statements Loops (for, while) break, continue, pass | 1 | 2026-01-15 | 2026-01-15
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Functions Defining functions Parameters & return values Lambda functions Recursion | 1 | 2026-01-16 | 2026-01-16
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-01-17 | 2026-01-17
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-01-18 | 2026-01-18
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Regex & File Handling Regular expressions (match, search, findall) File handling (read, write, append) Working with CSV & text files | 1 | 2026-01-19 | 2026-01-19
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Exception Handling Built-in exceptions try–except–else–finally Custom exceptions | 1 | 2026-01-20 | 2026-01-20
Left Shift Program 2026 | Power Skill 1 | Introduction to Power skills # Ice breaking, Objective setting # Communication skills (Modes and overview) # Introduction to written communication (dos and don’ts of emails) # Grooming (Hygiene Squad) | 1 | 2026-01-21 | 2026-01-21
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | OOP Basics Classes & objects Constructors Instance vs class variables | 1 | 2026-01-22 | 2026-01-22
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Inheritance & Polymorphism Inheritance types Method overriding Polymorphism concepts | 1 | 2026-01-23 | 2026-01-23
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-01-24 | 2026-01-24
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-01-25 | 2026-01-25
Left Shift Program 2026 | HOLIDAY |  | 0 | 2026-01-26 | 2026-01-26
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Advanced OOP & Modules Encapsulation & abstraction Python modules & packages Import mechanisms | 1 | 2026-01-27 | 2026-01-27
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Decorators & Generators Function decorators Class decorators Generators & yield | 1 | 2026-01-28 | 2026-01-28
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Threading Multithreading concepts Thread lifecycle Synchronization basics | 1 | 2026-01-29 | 2026-01-29
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | NumPy & Pandas NumPy arrays & operations Pandas Series & DataFrames Data filtering & aggregation | 1 | 2026-01-30 | 2026-01-30
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-01-31 | 2026-01-31
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-02-01 | 2026-02-01
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Flask Flask architecture Routes & request handling Templates & responses | 1 | 2026-02-02 | 2026-02-02
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | FastAPI FastAPI fundamentals Path & query parameters Request validation | 1 | 2026-02-03 | 2026-02-03
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | RESTful APIs REST principles CRUD operations API best practices | 1 | 2026-02-04 | 2026-02-04
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | API Testing & Git Postman for API testing Git basics (clone, commit, push, branch) | 1 | 2026-02-05 | 2026-02-05
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Deployment Basics Virtual environments Deployment fundamentals Environment configurations | 1 | 2026-02-06 | 2026-02-06
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-02-07 | 2026-02-07
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-02-08 | 2026-02-08
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Unit Testing with Pytest Testing concepts Writing test cases Fixtures & assertions | 1 | 2026-02-09 | 2026-02-09
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | CI/CD & GitHub Actions CI/CD pipeline basics GitHub Actions overview Automated testing flow | 1 | 2026-02-10 | 2026-02-10
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | Docker Containerization concepts Docker images & containers Dockerizing Python applications | 1 | 2026-02-11 | 2026-02-11
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | SQL & ORM SQL fundamentals CRUD operations ORM concepts (SQLAlchemy) | 0 | 2026-02-12 | 2026-02-12
Left Shift Program 2026 | Python Fullstack + Assignment + Use cases | NoSQL & Data Integration MongoDB basics CSV & JSON parsing Database testing basics | 1 | 2026-02-13 | 2026-02-13
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-02-14 | 2026-02-14
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-02-15 | 2026-02-15
Left Shift Program 2026 | CG M1 Assessment |  | 1 | 2026-02-16 | 2026-02-16
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Data Science Foundations Data Science & Jupyter Data Science overview & use cases Jupyter Notebook setup & workflow Working with datasets Hands-on: Notebook-based data exploration NumPy NumPy arrays | 1 | 2026-02-17 | 2026-02-17
Left Shift Program 2026 | Power Skill 2 | Language skills (Part1) # Introduction to parts of speech & Subject verb agreement and Articles # Content videos # Email Etiquette # Test(Email- application of SVA & Articles). # Activity bases learnings (role play activity) # Listening (questioning and probing) Language skills (Part2) # Tenses # Art of pronunciation (verbal’s skills) #using Co-pilot and ChatGPT | 1 | 2026-02-18 | 2026-02-18
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Array operations & broadcasting Indexing & slicing Hands-on: Numerical computations Pandas Series & DataFrames Data loading (CSV, Excel) Filtering, sorting, grouping Hands-on: Data wrangling tasks | 1 | 2026-02-19 | 2026-02-19
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Matplotlib & Probability Data visualization with Matplotlib Charts & plots Probability basics Distributions & real-world examples | 1 | 2026-02-20 | 2026-02-20
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-02-21 | 2026-02-21
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-02-22 | 2026-02-22
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Machine Learning Machine Learning Fundamentals What is Machine Learning Types of ML (Supervised, Unsupervised) ML workflow & data preparation | 1 | 2026-02-23 | 2026-02-23
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Regression Linear regression Multiple regression Model training & prediction Hands-on: Regression use case | 1 | 2026-02-24 | 2026-02-24
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Classification Logistic regression KNN, Decision Trees Classification metrics Hands-on: Classification model | 1 | 2026-02-25 | 2026-02-25
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Clustering K-Means Hierarchical clustering Distance metrics Hands-on: Clustering use case | 1 | 2026-02-26 | 2026-02-26
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Model Evaluation Train-test split Cross-validation Bias–variance tradeoff Evaluation metrics Pipelines & Feature Engineering Feature scaling | 1 | 2026-02-27 | 2026-02-27
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-02-28 | 2026-02-28
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-03-01 | 2026-03-01
Left Shift Program 2026 | HOLIDAY |  | 0 | 2026-03-02 | 2026-03-02
Left Shift Program 2026 | CG M1 Improvement Test |  | 1 | 2026-03-03 | 2026-03-03
Left Shift Program 2026 | HOLIDAY |  | 0 | 2026-03-04 | 2026-03-04
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Encoding techniques ML pipelines Hands-on: End-to-end pipeline scikit-learn scikit-learn architecture Model selection & tuning Hyperparameter tuning | 1 | 2026-03-05 | 2026-03-05
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Deep Learning & CV Neural Networks Fundamentals Perceptron Neural network architecture Activation functions Loss functions | 1 | 2026-03-06 | 2026-03-06
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-03-07 | 2026-03-07
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-03-08 | 2026-03-08
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Deep Learning with CNNs Convolution layers Pooling layers CNN architecture | 1 | 2026-03-09 | 2026-03-09
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Image Processing with OpenCV Image reading & manipulation Filters & transformations Edge detection | 1 | 2026-03-10 | 2026-03-10
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Image Classification Building image classifiers Training CNN models Model performance evaluation | 1 | 2026-03-11 | 2026-03-11
Left Shift Program 2026 | Python ML / DL + Assignment + Use cases | Advanced DL Use Cases Transfer learning overview Improving model accuracy Real-world CV applications | 1 | 2026-03-12 | 2026-03-12
Left Shift Program 2026 | Power Skill 3 | Presentation skills # Introduction to Presentation skills (setting objective) # Albert Mehrabian rule and communication styles # Rules of presentation (3 T’s) # Dos and Don’ts of presentation # Activity on presentation skills by YP’s | 1 | 2026-03-13 | 2026-03-13
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-03-14 | 2026-03-14
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-03-15 | 2026-03-15
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | Generative AI & LLM Foundations Generative AI overview & use cases Large Language Models (LLMs) Transformer architecture basics Tokenization & inference concepts | 1 | 2026-03-16 | 2026-03-16
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | Prompt Engineering Prompt design principles Zero-shot, few-shot prompting Chain-of-thought prompting Prompt optimization techniques | 1 | 2026-03-17 | 2026-03-17
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | Embeddings & Vector Databases What are embeddings Similarity search & semantic retrieval Vector databases overview Hands-on: Storing & querying embeddings | 1 | 2026-03-18 | 2026-03-18
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | Retrieval-Augmented Generation (RAG) RAG architecture & workflow Chunking strategies Context injection Evaluation considerations | 1 | 2026-03-19 | 2026-03-19
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | Model Fine-Tuning Fine-tuning vs prompting Parameter-efficient tuning (LoRA overview) Fine-tuning workflows Model performance comparison | 1 | 2026-03-20 | 2026-03-20
Left Shift Program 2026 | HOLIDAY |  | 0 | 2026-03-21 | 2026-03-21
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-03-22 | 2026-03-22
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | Agentic AI Fundamentals What is Agentic AI Agent roles & responsibilities Planning, reasoning & execution | 1 | 2026-03-23 | 2026-03-23
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | Multi-Agent Systems Single vs multi-agent architecture Agent communication patterns Task delegation strategies | 1 | 2026-03-24 | 2026-03-24
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | LangGraph LangGraph architecture Graph-based agent workflows State management Building multi-step agents | 1 | 2026-03-25 | 2026-03-25
Left Shift Program 2026 | HOLIDAY |  | 0 | 2026-03-26 | 2026-03-26
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | CrewAI CrewAI framework overview Role-based agent design Task orchestration & coordination | 1 | 2026-03-27 | 2026-03-27
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-03-28 | 2026-03-28
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-03-29 | 2026-03-29
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | AutoGen AutoGen concepts Conversational agents Agent-to-agent collaboration | 1 | 2026-03-30 | 2026-03-30
Left Shift Program 2026 | HOLIDAY |  | 0 | 2026-03-31 | 2026-03-31
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | Copilot Studio – Fundamentals Copilot Studio overview Creating AI agents Prompt flows & logic | 1 | 2026-04-01 | 2026-04-01
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | Copilot Studio – Enterprise Deployment Orchestration strategies Deployment in Teams & SharePoint GPT-powered workflows | 1 | 2026-04-02 | 2026-04-02
Left Shift Program 2026 | HOLIDAY |  | 0 | 2026-04-03 | 2026-04-03
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-04-04 | 2026-04-04
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-04-05 | 2026-04-05
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | Model Context Protocol (MCP) MCP concepts & architecture Agent–tool communication MCP SDKs & connectors | 1 | 2026-04-06 | 2026-04-06
Left Shift Program 2026 | GenAI / Agentic + Assignment + Use cases | MCP Integration Patterns Tool invocation via MCP Secure context sharing Enterprise agent integration use cases | 1 | 2026-04-07 | 2026-04-07
Left Shift Program 2026 | Power Skill 4 | Email communication # Objective setting on written communication # 7C’s (Email etiquette) # Email writing Test and activities # Accountability & Ownership # Teamwork | 1 | 2026-04-08 | 2026-04-08
Left Shift Program 2026 | Azure AI + Assignment + Use cases | Azure AI & Cloud Overview Azure AI ecosystem overview Azure OpenAI services Azure AI Studio AI workloads on Azure | 1 | 2026-04-09 | 2026-04-09
Left Shift Program 2026 | Azure AI + Assignment + Use cases | Azure OpenAI & AI Apps Deploying Azure OpenAI models Prompt flow in Azure AI Studio Building AI-powered applications Model endpoints & usage patterns | 1 | 2026-04-10 | 2026-04-10
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-04-11 | 2026-04-11
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-04-12 | 2026-04-12
Left Shift Program 2026 | Azure AI + Assignment + Use cases | Deployment, Security & Compliance AI application deployment strategies Identity & access management Responsible AI principles Security, privacy & compliance | 1 | 2026-04-13 | 2026-04-13
Left Shift Program 2026 | HOLIDAY |  | 0 | 2026-04-14 | 2026-04-14
Left Shift Program 2026 | Azure AI + Assignment + Use cases | Azure Cognitive Services – Overview Cognitive Services architecture Service categories & use cases API integration patterns | 1 | 2026-04-15 | 2026-04-15
Left Shift Program 2026 | Azure AI + Assignment + Use cases | Azure Bot Service Azure Bot Framework Conversational AI fundamentals Bot deployment & channels | 1 | 2026-04-16 | 2026-04-16
Left Shift Program 2026 | Azure AI + Assignment + Use cases | Document Intelligence & AI Search Azure Document Intelligence Form & document processing Azure AI Search fundamentals Indexing & semantic search | 1 | 2026-04-17 | 2026-04-17
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-04-18 | 2026-04-18
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-04-19 | 2026-04-19
Left Shift Program 2026 | Azure AI + Assignment + Use cases | MLOps Fundamentals ML lifecycle overview Model training & versioning Model monitoring & drift detection | 1 | 2026-04-20 | 2026-04-20
Left Shift Program 2026 | Azure AI + Assignment + Use cases | Azure ML & AIOps Azure Machine Learning workspace Pipelines & model retraining Introduction to AIOps concepts | 1 | 2026-04-21 | 2026-04-21
Left Shift Program 2026 | Azure AI + Assignment + Use cases | Azure AI Foundry Azure AI Foundry overview Enterprise AI deployment patterns Integration with existing systems | 1 | 2026-04-22 | 2026-04-22
Left Shift Program 2026 | Azure AI + Assignment + Use cases | Enterprise Integration & Best Practices End-to-end Azure AI architecture Scaling AI solutions Governance & operational best practices | 1 | 2026-04-23 | 2026-04-23
Left Shift Program 2026 | Azure Data Engineering & Analytics + Assignment + Use cases | Azure Data Factory – Fundamentals Azure Data Factory overview & architecture Data pipelines & activities Linked services & datasets | 1 | 2026-04-24 | 2026-04-24
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-04-25 | 2026-04-25
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-04-26 | 2026-04-26
Left Shift Program 2026 | Azure Data Engineering & Analytics + Assignment + Use cases | Pipelines, Triggers & Integration Runtime Pipeline orchestration Triggers (schedule, event-based) Integration runtime types Hands-on: Pipeline creation | 1 | 2026-04-27 | 2026-04-27
Left Shift Program 2026 | Azure Data Engineering & Analytics + Assignment + Use cases | Monitoring & Management Pipeline monitoring Debugging failures Logging & alerts Performance optimization | 1 | 2026-04-28 | 2026-04-28
Left Shift Program 2026 | Azure Data Engineering & Analytics + Assignment + Use cases | PySpark Basics Apache Spark overview RDD concepts Spark architecture Basic transformations & actions | 1 | 2026-04-29 | 2026-04-29
Left Shift Program 2026 | Azure Data Engineering & Analytics + Assignment + Use cases | DataFrames & Spark SQL Spark DataFrames DataFrame operations Spark SQL queries Hands-on: Structured data processing | 1 | 2026-04-30 | 2026-04-30
Left Shift Program 2026 | HOLIDAY |  | 0 | 2026-05-01 | 2026-05-01
Left Shift Program 2026 | Revision + Weekly Assessment |  | 1 | 2026-05-02 | 2026-05-02
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-05-03 | 2026-05-03
Left Shift Program 2026 | Azure Data Engineering & Analytics + Assignment + Use cases | Microsoft Fabric Microsoft Fabric architecture Lakehouse & OneLake Data Activator Real-time analytics | 1 | 2026-05-04 | 2026-05-04
Left Shift Program 2026 | Azure Data Engineering & Analytics + Assignment + Use cases | Power BI – Data Modelling & DAX Power BI architecture Data modelling concepts Relationships DAX fundamentals | 1 | 2026-05-05 | 2026-05-05
Left Shift Program 2026 | Azure Data Engineering & Analytics + Assignment + Use cases | Visualization & Publishing Visualizations & dashboards Report design best practices Publishing & sharing reports Power BI integration with Fabric | 1 | 2026-05-06 | 2026-05-06
Left Shift Program 2026 | Power Skill 5 | Team work and accountability # Listening, Questioning & Probing # Meeting Etiquette # Interview Skills #Comprehensive Test (Email, Grammar, Behavioural) | 1 | 2026-05-07 | 2026-05-07
Left Shift Program 2026 | SPRINT - Capstone Project Implementation |  | 1 | 2026-05-08 | 2026-05-08
Left Shift Program 2026 | SPRINT - Capstone Project Implementation |  | 1 | 2026-05-09 | 2026-05-09
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-05-10 | 2026-05-10
Left Shift Program 2026 | SPRINT - Capstone Project Implementation |  | 1 | 2026-05-11 | 2026-05-11
Left Shift Program 2026 | SPRINT - Capstone Project Implementation |  | 1 | 2026-05-12 | 2026-05-12
Left Shift Program 2026 | SPRINT - Capstone Project Implementation |  | 1 | 2026-05-13 | 2026-05-13
Left Shift Program 2026 | SPRINT - Capstone Project Implementation |  | 1 | 2026-05-14 | 2026-05-14
Left Shift Program 2026 | CG SPRINT EVALUATION |  | 1 | 2026-05-15 | 2026-05-15
Left Shift Program 2026 | Revision on Data and AI |  | 1 | 2026-05-16 | 2026-05-16
Left Shift Program 2026 | SUNDAY |  | 0 | 2026-05-17 | 2026-05-17
Left Shift Program 2026 | Revision on Data and AI |  | 1 | 2026-05-18 | 2026-05-18
Left Shift Program 2026 | Revision on Data and AI |  | 1 | 2026-05-19 | 2026-05-19
Left Shift Program 2026 | Revision on Data and AI |  | 1 | 2026-05-20 | 2026-05-20
Left Shift Program 2026 | Revision on Data and AI |  | 1 | 2026-05-21 | 2026-05-21
Left Shift Program 2026 | L1 Capgemini Assessment |  | 1 | 2026-05-22 | 2026-05-22